## Sheet1
| SBIRT Task | Person(s) accountable | Steps taken | Status (red/yellow/green)
First 3 months
1 | Organizational self assessment: What are the key gaps in the current state vs. desired future state.
2 | Secure commitment from key leaders in the organization whose support is critical in effecting changes needed to achieve success. Ensure allocation of time and resources necessary for effective, sustainable SBIRT implementation.
3 | Engage policymakers to support SBIRT, as needed. For example, the state Medicaid Director may need to activate the SBIRT billing codes and intervene if there is difficulty securing reimbursement for SBIRT services. State or local elected officials may need to approve budget allocations or changes in statutes.
4 | Select and empower multidisciplinary Core Implementation Team. Discuss the identified key gaps and planned approach to change. Determine a consistent meeting schedule, create implementation timeline and plan for ongoing communications among the team, with leadership and with broader staff.
5 | Establish a first draft workflow of tools, targets, tasks and roles for providing SBIRT services. Decide initial pilot scope and population including age range, location/dept/site and provider/team champions.
6 | Leaders kick off initial pilot via training, announce start date and plan for regular huddles to review performance.
7 | Conduct first PDSA of workflow, problem solve barriers, identify facilitators of efficiently providing the desired care, gather data.
Months 4 through 7
8 | Revise workflow to reflect lessons learned from first PDSA.
9 | Continue small tests of change and review data frequently.
10 | Leadership support the importance of the work by overseeing iterative improvement and reviewing progress monthly. Communicate expectations to leaders at all levels regarding importance of QI. Continually spread positive stories.
11 | Identify additional resources needed for full implementation, such as partnerships with treatment programs or other specialty care and community services, expanding services for Medication Assisted Treatment, peer recovery specialists, etc.
12 | Create/purchase education, promotional and engagement materials such as posters, brochures and other tools.
13 | Refine measurements critical to evaluating success of both patients and the organization. Establish frequency, source and methodologies for collecting, analyzing and sharing data. Align with required quality metrics. Include SBIRT in continuous quality improvement processes to provide feedback on a frequent and routine basis.
Months 8 through 12
14 | Create a plan for further dissemination and spread – adding sites/providers/patient populations. Include communication and value messaging based on data and lessons learned from pilot.
15 | Prepare for ongoing training and development including on-boarding new staff, evidence updates, etc.
16 | Develop protocol to including required screenings and interventions, referrals, documentation, invoicing, & follow-up. Also procedures for continual monitoring of processes, outcomes, and costs.
17 | Launch clinical change to the remainder of the practice.
18 | Estimate costs and revenue per month of alcohol and/or other drug use care (screening, assessments to elicit symptoms, brief counseling, and care management) and calculate revenue/cost ratio.
19 | Have a plan for meeting at least twice a year to review costs and revenue for providing alcohol- and other drug-related care.
20 | Integrate SBIRT protocols with existing P&P so that SBIRT becomes an integral part of service delivery, not an add-on service.